## Tasks and Timeline (hidden)
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F

## Task Brainstorm
Task Brainstorm
| Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
1 | Milestone: Tablet Sourcing & Procurement
1.1 | Research and identify different tablet vendor websites and packages offered
1.2 | Test out tablet systems and offered packages
1.3 | Generate quotes and review costs of tablets | **Custom branding, design, and upload are separate vendor offerings
1.4 | Select the tablet option and vendor | Work with rollout location GMs (North & Downtown) to determine exact number of tablets required for pilot
1.5 | Finalize sevice package with the vendor
1.6 | Vendor timeline and delivery schedule
1.7 | Create contracts and statements of work for vendors
2 | Milestone: Tablet customization
2.1 | Update the menu interface to match the branding and layout of current menus | Connect Seydou with marketing department-tablet menu interface to look and feel like the printed hardcopy menus.
2.2 | Customize tablet features to suggest any menu item as an add-on | Suggesting items that have the highest profit margins
2.3 | Enable coupons or daily specials offers | Offering specific items; Also, provide picture representation of menu items
2.4 | Enable customization and tracking of guest orders | Ensure special requests and choices are recorded and communicated to the kitchen staff
2.5 | Communication directly to the kitchen | this is a standard feature on all current tablet models
2.6 | Enable real time update in menu from the admin back-end of the software | this is a standard feature on all current tablet models
2.7 | Implement a post-dining survey to assess customer satisfaction | feedback option is offered with the payment screen, which includes a default tip of 20 percent.
2.8 | Enable "customer led opt-in" for rewards program and mailing list
2.9 | Preauthorize credit cards to open tabs | Create messaging about payment portal security to display on the tablets, This would be limited to bar area only for current rollout
3 | Milestone: Integrate the tablet package with existing POS and host software | requires testing- run diagnostics.
4 | Milestone: Tablet Security- Digital and Physical
4.1 | Secure payment gateway | Cybersecurity- use point-to-point data encryption, and oversee network activity for abnormalities
4.2 | Enable GPS location services on each tablet
4.3 | Create a procedure for securing tablets at the end of the night (at the table or in a safe)
5 | Milestone: Tablet installation
5.1 | Map out seating chart/upload into software | Identify where at the bar, & total tablets are to be installed- GMs to provide the total number
5.2 | Identify tablet position on the table for optimum table space utilization | ** possible mounted at the end of the table
5.3 | Coordinate with Electrician to hardwire the tablets | Tablet vendor to get an electrician
5.4 | Software installation of the tablets at each table
5.5 | Test run Tablet system for connection and software issues | Run diagnostics- create a feedback loop to identify areas of improvement desired in the technology
6 | Milestone: Employee Training
6.1 | Schedule staff meetings with the GM to get staff buy-in before roll out | Has to come in from GMs for the staff; take note of staff's concerns and fears with regars to the tablet launch
6.2 | Schedule a training for GMs | Coordinate with Alex for scheduling for Downtown and Gilly for North location.
6.3 | Training for waitstaff | Designate specific employees as trainers, who will help onboard the rest of employees
6.4 | Invite friends and family & mimic full service as test run | to see if there are any issues
Streamline the ordering process,the payment and tipping process
Create a launch day plan: staffing, troubleshooting, etc.

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
How to Increase Your Restaurant’s Profits in 2023 | https://www.business.com/articles/how-to-increase-restaurant-profits/ | 2023-05-11 | 1.Start by investing in a food waste tracker. These devices measure food and have a camera that monitors food waste so you can keep an eye on what’s being thrown away (and determine why).
2.Another way to cut down on food waste is to redesign your menu, focusing only on making what you do best.
3.A restaurant management system will help you keep track of sales, manage employees and create a rewards program or mailing list for your customers
Restaurant inventory software will let you track every ingredient you use & keep an eye on expiration dates
to increase your restaurant patronage using Social media marketing. Utilize social media management apps that allow you to schedule when a post will go live and give you insight on the perfect time to upload your #foodpics so you can reach the largest audience.
Having welcoming staff at the door to greet them and get them situated can make a positive first impression. In addition, having staff thank customers on their way out may encourage them to return soon. Customers who feel welcomed and appreciated are more likely to generate positive reviews and recommend the restaurant to people they know.
To create a successful menu that will generate profit, learn which meals customers want. Consider your restaurant’s location, which types of foods sell well in the area and what people are ordering the most from your current menu.
If you find that something isn’t selling well, try reworking the dish or creating new options. Customer survey data can provide valuable feedback. Additionally, have managers or waitstaff visit tables during service times and chat with customers about their opinions on certain dishes.
In addition to a website, restaurants should create a social media presence to promote their restaurant and communicate with a broader audience.
Customer loyalty programs demonstrate that you value your patrons. To bring in new customers, consider offering coupons or daily specials to encourage them to stop in and experience your restaurant.
Small Business Guide to a Restaurant Management System | https://www.business.com/articles/restaurant-management-system-guide/ |  | A restaurant management system is a type of point-of-sale (POS) software specifically designed for restaurants, bars, food trucks and others in the foodservice industry.
RMS encompasses all back-end needs, such as inventory and staff management. These systems also handle payment processing, order management and other tasks staff would typically perform.
an RMS offers features unique to the foodservice industry like ingredient-level inventory updates, the ability for waitstaff to send orders directly from the table to the kitchen, split billing and kitchen displays
with an RMS Restaurants can perform these tasks:
1. Track sales and orders
2.View accurate, real-time financial statements
3.Manage staff scheduling
4.Access data through the cloud
5.Utilize a built-in customer relationship management (CRM) tool to build mailing lists or start a rewards program
With an end-to-end system, you will have complete access to these functions and features:
Employee schedules, including daily, vacation and sick time
Payroll
Financial statements
Inventory
Accounting
Reporting and analytics
Core POS
CRM
Menu
Reservations
Determine what type of system you need.
If you have plans to grow or franchise your restaurant, buy a system that can grow with it. Make sure your system can handle an increase in the number of terminals and handheld devices, provides advanced large-scale analytics, offers multibranch add-ons and can handle a large number of employees (and their schedules).
Order management
Your restaurant staff should be able to manage tables, reservations, checks and menu items easily through your RMS
managers should also be able to control refunds, voids and comps and view order statuses.
|  |  | If you operate a bar, your RMS should allow you to preauthorize credit cards to open tabs. | important feature for rollout, could be a task
provides a seamless experience for both customers and staff, eliminating the risk of human error and ensuring all information is in one place
Reporting and customer data
Understanding your customers will help you better target them through advertising and personalizing their dining experiences.
Consider a system that offers marketing tools, such as promotions and loyalty or rewards programs. Your RMS may have native marketing tools or require third-party software integration for this. If you’re interested in offering gift cards for your restaurant, make sure your RMS can help you manage that as well.
How to Attract Customers to Your Restaurant | https://www.business.com/articles/how-to-attract-customers-to-your-restaurant/ |  | Sign up for a Google Business Profile.
If you don’t have a website yet, or even if you have, signing up for a Google Business Profile has so many advantages for your restaurant. For starters, it makes it easy for customers to find your store location. You can also obtain better search visibility and gain access to a wealth of analytics
Encourage more spending:
1. Suggesting items that have the highest profit margins.
2. Offering a variety of extras that could accompany the meal ordered by your customer.
3. Offering specific items. For instance, if offering a drink, be specific about what beverage it is (iced tea, cola, orange juice, etc.).
Run promotions.
offer a free meal for every group of five on days when you have the least number of customers, provide free drinks every Friday night or provide a comp dessert for customers celebrating their birthdays at your restaurant.
Loyalty programs
Tap into your customers’ FOMO (fear of missing out) by showing them exactly what they are missing. Offer free food. Customers love free stuff, whether it’s a complimentary drink, pastry or dessert, or an appetizer.
Tabletop tech speeds up service and boosts profits, study says | https://www.restaurantdive.com/news/tabletop-tech-speeds-up-service-and-boosts-profits-study-says/560152/ |  | Any technology with internet connection also comes with the added risk of consumer data breaches,
|  |  | Experts advise restaurants to proactively think about cybersecurity when building up their plans, oversee network activity for abnormalities and use data encryption. | important feature for rollout, could be a task
Seven Ways Tablets Are Changing Restaurant Customer Experience | Seven Ways Tablets Are Changing Restaurant Customer Experience – InMoment |  | Enhanced Interaction- restaurants are exploring the use of promotional content or pay-as-you-go games that provide entertainment or customer engagement opportunities while guests wait for their food to arrive. These kinds of activities drive bottom-line improvements by leveraging customer experiences to increase loyalty.
“On the Fly” Data Insights :
Tablets offer a non-threatening and engaging resource that restaurants can use to capture customer insights. While many guests are hesitant to provide personal information when they pay their bills or at the request of their servers, they are less resistant to providing data on their own terms, especially if the submission of data is tied to a discount or contest. Multi-site restaurants can leverage tablets to capture data insights at the local level, helping them tailor the customer experience to the desires and preferences of local consumers.
Guest Reviews
A great time to capture guest reviews is before they leave the restaurant, while details of the experience are top of mind. Willingness to provide feedback is also much greater with this immediacy, since even the most satisfied guests often don’t feel compelled to rate their experience later.
Reviews captured via tablets can then be used to build brand reputation and modify the customer experience based on guests’ suggestions.
Multichannel Feedback
Surveys and other tools delivered on tablet devices create feedback that can be shared across all available channels, increasing the impact of brand advocacy and positive mentions. In particular, restaurants need to prioritize the use of tablets to capture feedback that can be distributed via social channels.
Enhanced Employee Engagement
One of the largest challenges with customer feedback is how to use the results when they arrive. Tablets can help to reshape this challenge by bringing results to life in a meaningful way to customer facing staff. Data visualization capabilities on tablets are extensive,
presents it in a meaningful way that motivates staff and will drive guest experience improvement.
Why Tablets on Restaurant Tables Are Here to Stay | Why Tablets on Restaurant Tables Are Here to Stay - Eater |  | tips have stayed steady or even increased, thanks to the ease of tipping via tablet: Diners can typically tap just one button to automatically apply a tip of the industry standard 20 percent, which is easier than manually entering a smaller tip. Tips are likely also higher thanks to diners’ increased satisfaction with service
Restaurants are also seeing increased check averages when tablets are in use.
because diners can now order it with just a touch of a button — eliminating any potential sheepishness that may come
**Chili’s, and a number of other chains, claims its clients have seen a 30 percent overall increase in dessert sales.
tabletop tablets are also serving as a valuable data gathering tool. Presenting a post-meal survey for diners to fill out electronically as part of the payment process provides the restaurants with useful feedback on food and service, and in some cases guests who want to provide more specific feedback — such as complaining about cold fries or praising a staff member — can send emails directly to management, which is a much smaller hurdle than actually flagging down a manager to speak to face-to-face.
How Tablets are Revolutionising Restaurant Service | How Tablets are Revolutionising Restaurants - Bouncepad |  | According to an article from Bloomberg Businessweek and Vanessa Wong in 2013, Ziosk was already seeing an impressive 20 percent increase in appetizer sales and a 30 percent increase in dessert sales. This increase in sales meant bigger checks and bigger tips. With default settings like suggested tipping percentages – as seen in cabs – customers are prompted to actively select the tip amount, leaving both the customer and wait staff happy.
Restaurants are Using Digital Menus to Gain a Competitive Advantage | Restaurants are Using Digital Menus to Gain a Competitive Advantage |  | Digital Tablet Menu Features
Digital tablet menus offer many benefits:
Provide picture representation of menu items and support cross sale and up sale
Ensure special requests and choices are recorded and communicated to the kitchen staff
Allow diners to track progress of food preparation
Provide the restaurant the ability to update the menu in real time and remove sold out offerings
Provide diners with information on the restaurant, dishes, chefs, past patrons, local attractions and more
Streamline the ordering process
Streamline the payment and tipping process
Enable feedback
Digital menus can send direct, timely, customer-relevant marketing material and product information to patrons. The use of technology enables further customer engagement and allows restaurants to publish content for diners. Customer loyalty can be built by enhanced interaction and educating of the customer. It can track previous orders and encourage trying other dishes in the future. Diners have the opportunity to learn more about the dishes, restaurant, location, history and other interesting facts to supplement a positive dining experience. This positive experience and guest engagement along with the ease of signing up for loyalty programs digitally leads to customers being 10 times more likely to sign up to a loyalty club when through a digital menu. (Chili’s rollout)
Best Practices for Your Digital Menu | https://www.barandrestaurant.com/operations/best-practices-your-digital-menu |  | Where does your bar’s digital presence start? With your online menu. Your online menu serves as the launching point for the rest of your digital experience, just as your physical menu is the jump off point for your customers’ in-person experience at your bar.
A great online menu incorporates all the new tools that you and your customers adopted over the past year — tools like QR codes, online ordering, and cashless payments — and put them in one place for the easiest contactless dining experience possible.
important feature for rollout, could be a task
Customers expect your digital menu to be optimized to the dimensions and hardware of mobile phones, because that is primarily how they will be accessing them.
craft your menu design to work best in the palm of your customer’s hand.
Connect your menu to a dynamic QR code
QR codes make it a breeze for customers to pull up your online menu on their phones.
Make sure you use dynamic QR codes, though, because they can be updated. That way you can swap designs, change links, and update menus without having to print all new QR codes.
How to enhance service with tabletop tablets | https://www.restaurantbusinessonline.com/technology/how-enhance-service-tabletop-tablets |  | interact with the guests, using technology as a complement to the employee
Tablets also have a ‘Call Server’ button, so there’s always a way to grab the staff.
The interactive screen of the tablet is used to showcase new items
It’s easier to update than print menus, making tablets ideal for promotions.
7 Vital Steps in a Successful Restaurant Technology Rollout | https://qsrautomations.com/blog/restaurant-technology/7-vital-steps-technology-rollout/ |  | If you have multiple sites, you should also identify your training team. Designate specific employees as trainers, who will help onboard the rest of employees and be a go-to person for any issues or fixes. Provide ongoing training so that employees can achieve the full potential of the software you’ve been rolling out.
As you implement, create a feedback loop to identify areas of improvement you would like to see in the technology. This communication channel is especially crucial for more customizable and scalable solutions.
Restaurant reboot | https://www.pmi.org/learning/library/restaurant-reboot-9754 |  | most restaurant IT projects include analytics features that let owners track business trends in real time in order to improve service while cutting costs.
The final version of the FoodSave technology developed by Winnow Solutions features a scale and digital dashboard allowing kitchen staff to sort and weigh discarded food into categories, including inventory or spoilage damage, trimmings, cooking errors, unused prepared food and plate waste. “Being able to classify different kinds of waste was half the challenge,” Ms. Moorhouse says. Winnow customized the system based on a restaurant's ingredient costs, allowing it to convert wastage data into a monetary value.
Once kitchen staff got into the habit of sorting waste, owners could create daily reports about how and where waste was being generated—and then implement targeted solutions.
Tablets To Provide Secure Payments In US Restaurants | https://www.forbes.com/sites/robertvamosi/2015/02/19/tablets-to-provide-secure-payments-in-us-restaurants/?sh=3ede9b5a1992 |  | provide point-to-point encryption,
feedback option is offered with the payment screen, which includes a default tip of 20 percent.
5 Things That Tabletop Tablets for Bars Can Do | https://get.buzztime.com/step-by-step-guide-to-tabletop-tablets-for-bars/

## Quality and Evaluation (hidden)
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions (hidden)
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5