## Dashboard
ABC Companys: Operations & Training Plan
Description: This is a document resource overview for the Operations and Training plan for ABC Companys service.
Owner: Project Manager name
Status: Draft
Key Docs | Description
Project charter | An overview of the project, key elements and expectations
Statement of work | Identifies the work that is included in the project and the pricing that was quoted initially.
Risk management plan | Identifies the potential risks to the project, their likelihood, and how you plan to mitigate them if they become realized.
Schedule | Identifies the planned schedule as well as any changes through out the project lifecycle.
Budget | Identifies the planned budget as well as any over and under runs. Allows you to estimate the cost at completion.
Communication plan | Identifies how often, what type of communication method, and what information your stakeholders needs to know
Shared folder | Folder with all relevant documentation
RACI chart | Identifies who is responsible, accountable, consulted and informed within the project.
Note on A7: Add hyperlink to digital document, Project charter
Note on A8: Add hyperlink to digital document, Statement of work
Note on A9: Add hyperlink to digital document, risk management plan
Note on A13: Add hyperlink to a shared folder
Note on A14: Add hyperlink to RACI chart spreadsheet

## Project Schedule
ABC Company
Gantt Chart
TITLE: ABC Companys Operations and Training Plan | [6 empty] | COMPANY NAME: |  |  |  |  | ABC Company
PROJECT MANAGER: Project Manager | [6 empty] | CREATION DATE: |  |  |  |  | 02/15
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Establish a plant delivery and logistics plan | [5 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
1.1 | Source packaging materials | Fulfillment Director | 3/1 | 3/12 | 10 | 0% | bar: MARCH M 1 to MARCH F 12
1.2 | Hire delivery drivers | HR Specialist | 3/15 | 3/26 | 10 | 0% | bar: MARCH M 15 to MARCH F 26
1.3 | Calculate delivery fees | Financial Analyst | 3/29 | 4/9 | 10 | 0% | bar: MARCH M 29 to APRIL F 9
2 | Select and install supply chain software and equipment
2.1 | Supervise vendor setup of inventory management and fulfillment software | Inventory manager | 4/12 | 4/14 | 3 | 0% | bar: APRIL M 12 to APRIL W 14
2.2 | Supervise vendor installation of fulfillment equipment | Fulfillment Director | 4/15 | 4/16 | 2 | 0% | bar: APRIL R 15 to APRIL F 16
2.3 | Determine internal safety protocols for equipment | Quality Assurance Tester | 4/19 | 4/30 | 10 | 0% | bar: APRIL M 19 to APRIL F 30
3 | Develop and launch an employee training program
3.1 | Develop training sessions | HR Specialist | 5/3 | 5/14 | 10 | 0% | bar: MAY M 3 to MAY F 14
3.2 | Train employees to use the software and equipment | Training Manager | 5/17 | 5/28 | 20 | 0% | bar: MAY M 17 to MAY F 28
3.3 | Monitor employee progress and improve training processes | Training Manager | 5/31 | 6/11 | 10 | 0% | bar: MAY M 31 to JUNE F 11

## Budget
Budget: ABC Companys Operations & Training
[7 empty] | TARGET BUDGET | ACTUAL/FINAL SPEND | UNDER/ OVER
[7 empty] | 62000 | 0 | 62000
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE | HOURS | RATE | UNITS | $/UNIT(S)
Milestone 1: Establish a plant delivery and logistics plan
Task 1: Purchase delivery trucks | -- |  |  | 2 | 15000 |  | 30000 |  | -30000
Task 2: Source packaging materials | -- |  |  | 1500 | 2 |  | 3000 |  | -3000
Task 3: Pay delivery drivers | Delivery Drivers (2) | 160 | 15 |  |  |  | 2400 |  | -2400
[6 empty] | Total | 35400 | 0
Milestone 2: Select and install supply chain management software and equipment
Task 1: Source vendor (includes set up, installation, and deployment of systems) | -- |  |  |  |  | 15000 | 15000 |  | -15000
[6 empty] | Total | 15000 | 0
Milestone 3: Develop and launch an employee training program
Task 1: Develop training sessions | HR Specialist | 80 | 50 |  |  |  | 4000 |  | -4000
Task 2: Train employees to use the software and equipment | Training Manager | 80 | 25 |  |  |  | 2000 |  | -2000
Task 3: Monitor employee progress and improve training processes | Training Manager | 80 | 25 |  |  |  | 2000 |  | -2000
[6 empty] | Total | 8000 | 0
Reserve buffer | [6 empty] | 3600
TOTAL | [6 empty] | 62000 | 0

## Communication Plan
ABC Company: Employee Training Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Planning Meeting | Daily | Project Manager | Every day at 3pm | In Person | Project planning and task updates to make sure the team stays on track | N/A | If needed, check in with manager about any high-level questions before meetings.
Software and Equipment Vendor | Planning Meeting | One time | Core Team: HR Specialist & Training Manager | Half day, Friday before development of the training plan begins; confirm date and time three days in advance | In Person | Go over the training manual in order to create an effective training plan for ABC Company's employees | N/A | This meeting needs to take place before the end of the vendor's SoW. Make sure the HR Specialist & Training Manager check in with fulfillment and inventory team members about the outcome of the meeting.
Human Resources | Planning Check-In | Weekly | Core Team: HR Specialist | Also send reminders (via email) the day before each training | In Person | Project planning assistance; provide support during the training session | N/A | Additional communication on an as-needed basis
Facilities | Planning Check-In | Weekly | Core Team: Administrative Coordinator | Tuesdays at 2pm | Phone Call | Reserve rooms, spaces, and equipment needed for employee training | N/A
Print Shop | Planning Check-In | Weekly | Core Team: Administrative Coordinator | Thursdays, including the day before the event | Phone Call | Coordinate on the printing and delivery of training manuals for employees | N/A
ABC Company employees | Informational Update | Weekly | Core Team: Training Manager | Fridays, including the Friday before training sessions begin | Email (from company address) | Communicate schedules, locations, and other necessary details to trainees | N/A | Set up automated reminder emails
ABC Company employees | Training | Daily | Core Team: Training Manager | Each day for ten days, starting at 10am | In Person | Train employees to use the supply chain management software and equipment | N/A
ABC Company employees | Survey | One time | Core Team: Training Manager | The first business day after trainings end, with two follow-up reminders | Email (from company address) | Post-training survey | N/A | Discuss results at next team meeting
Your Manager | Status Update | Weekly | Project Manager | Monday afternoons at 2pm | In Person | Update on event planning, ask questions, and get feedback | N/A | Come prepared with a brief update and specific questions
Senior Leaders: Director of Operations and the Director of Product (and CC your manager) | Status Update | One time | Project Manager | Debrief the week after the event | Email (from individual address) | High-level information and general updates | N/A