## Status Report
Project Name: ABC Companys Operations
Today's date: July 5
Summary |  |  |  | Overall Status (RAG)
We have installed new software to keep track of incoming orders and begun sending out the first test batch of ABC Company's products to customers. However, we have run into issues with product quality, customer communication, and the delivery process. Our next milestones include sending the test batch customers newsletters on plant upkeep and sending out the second batch of plants. This report also includes top risks and issues that have arisen and how we intend to take action. |  |  |  | Amber
Completed Milestones and Tasks
Description | Date | Status | Owner |  | Comments
Purchased and installed new software to keep track of incoming orders | June 15 | Completed | IT Specialist |  | The installation took three days longer than expected.
Began sending test batches of ABC Companys orders to customers | June 21 | Completed | Fullfillment Director |  | The number of orders exceeded targets by 15%.
Upcoming Milestones and Tasks
Description | Date | Status | Owner |  | Comments
Send the first batch customers e-newsletters with a tutorial on caring for their plants. | July 7 | Upcoming | Customer Service Manager |  | The newsletter must follow ABC Company’s brand design guidelines.
Hit at least 95% of delivery dates on time. | July 19 | Upcoming | Fullfillment Director |  | The error rate should be under 5%
Top Risks and Issues
Issue |  | Impact | Action |  |  | Owner
The warehouse team reports that 10% of the plants were not properly potted |  | Profit loss, complaints, and budget issues | Evaluate and adjusting plant potting process |  |  | Warehouse operations manager
The customer relations team is receiving only 30% of requests and complaints |  | Customer dissatisfaction | Fix problems with new customer service software |  |  | IT Specialist
The current delivery completion rate is only 80% |  | Cancelled subscriptions | Hire and train more delivery drivers |  |  | HR Specialist