## Slide 1
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Notes
MMM | Owner | H | L | Invested in the project but not with day-to-day operation
AAA | Director of Operation | H | H | Directly work with project manager
BBB | Executive Chef | H | M | Interest in project but not involved in day-to-day decision-making
CCC | Manager of North Location | M | H | Directly involved in restaurant operations and work closely with project manager, but less influence than CEO and Director of Operations
DDD | Manager of Downtown Location | M | H | Directly involved in restaurant operations and work closely with project manager, but less influence than CEO and Director of Operations
EEE | Manager of Waterfront Location | L | L | Provide reference information, however waterfront location is not involved in this project activity
FFF | Kitchen Manager of North Location | L | H | Directly work with tablet with high interest with project, but less influence than General Manager of Store
HHH | Kitchen Manager of Downtown Location | L | H | Directly work with tablet with high interest with project, but less influence than General Manager of Store
KKK | Restaurant Consultant | M | H | As restaurant technology consultant work closely with project team and project manager, his power is moderate
Stakeholder Analysis

## Slide 2
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
Power
high
low
med
high
low
MMM
Owner
AAA
Director of Operations
BBB
Exec. Chef
CCC
GM - North
DDD
GM - Downtown
FFF
Kitchen Manager - North
HHH
Kitchen Manager - Downtown
KKK
Restaurant Consultant
Interest
med
EEE
General Manager - Waterfront