## Tasks and Timeline
XYZ Company Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Procure Tablets
Work with GM @ Downtown location to identiy number of tablets needed. |  |  |  | 0 | PPP | bar: WEEK 1 M
Work with GM @ North location to identify number of tablets needed. |  |  |  | 0 | PPP | bar: WEEK 1 M
Determine if we will purchase and store backup tablets for emergencies |  |  |  | 0 | PPP | bar: WEEK 1 M
Assess available tablet options and specs from the supplier that meet requirements. |  |  |  | 0 | PPP | bar: WEEK 1 M
Create contract and statements of work for tablet vendor |  |  |  | 2 | PPP | bar: WEEK 1 T to WEEK 1 W
Buy and receive the correct number of tablets | Due to disruption in supply line, our originally ordered tablets were unable to arrive in time for launch and should come in a few weeks after launch. |  |  | 10 | PPP | bar: WEEK 1 W to WEEK 3 T
Milestone: Prepare for rollout w/ Internal Teams
Connect marketing team with Terrific Tablets for branding and digital menu design |  |  |  | 0 | PPP/KKK | bar: WEEK 1 W
Work with Carter on possible menu revamp | Is this something that we can hold off on? It potentially blocks the decision for featured menu items and coupon values to display on the tablets |  |  | 10 | BBB | bar: WEEK 1 W to WEEK 3 T
Add featured menu items and coupon values to tablets | Dependent on marketing team designs, as well as identifying featured menu items and coupon values from PPP. Would also be impacted by potential menu revamp from BBB. |  |  | 1 | AAA, BBB, Marketing | bar: WEEK 3 T
Work with tablet supplier to identify common issues and turn-around times resolving tablet problems. |  |  |  | 2 | PPP | bar: WEEK 1 R to WEEK 2 F
Develop internal policy and troubleshooting guides for the tablet rollout and usage |  |  |  | 3 | PPP | bar: WEEK 1 R to WEEK 2 F
Assess work required to ensure tablets integrate seamlessly with existing POS and host system | In order to work with the tablets, the FlatPlate OS needs to be on version 3.0 |  |  | 3 | bar: WEEK 1 F to WEEK 2 F
Milestone: Tablet Training
Develop a training program and rollout guide |  |  |  | 7 | PPP/KKK | bar: WEEK 1 R to WEEK 2 F
Pre-training meeting to introduce tablets and changes |  |  |  | 1 | KKK | bar: WEEK 1 F; WEEK 2 W to WEEK 2 F
Seydou will train GMs and key staff on tablets |  |  |  | 2 | KKK
Work with GMs to coordinate, schedule, and hold meetings to discuss rollout and report questions/concerns | Be sure to monitor staff response and address any questions |  |  | 7 | bar: WEEK 2 M to WEEK 4 T
Milestone: Tablet Installation
Identify bar section tables that need to be wired properly by electrician |  |  |  | 0 | CCC/DDD | bar: WEEK 3 T
Install one tablet to ensure proper installation and to identify any potential issues |  |  |  | 0 | CCC/DDD | bar: WEEK 3 T
Hire electrician to wire appropriate tables at Downtown location | half-days. Let's address any potential issues by intsalling one tablet first and note any issues. |  |  | 3 | bar: WEEK 3 T to WEEK 3 R
Hire electrician to wire appropriate tables at North location | half-days. Let's address any potential issues by intsalling one tablet first and note any issues. |  |  | 3 | bar: WEEK 3 T to WEEK 3 R
Milestone: Test Run
Hold test run with staff family and friends in order to mimic full service |  |  |  | 0 | bar: WEEK 3 F
Collect feedback from test run and identify ways to improve |  |  |  | 1 | bar: WEEK 3 F
Implement feedback from test run |  |  |  | 3 | bar: WEEK 3 F to WEEK 4 T
Milestone: Launch Day
Schedule launch day |  |  |  | 0 | bar: WEEK 1 M
Prepare for launch day by coordinating and identifying outstanding needs from GMs |  |  |  | 2 | bar: WEEK 3 R to WEEK 3 F
Launch day :D |  |  |  | 0 | bar: WEEK 4 T
Milestone: Install Upgraded Devices Post-Launch
Change plugs for new tablets. | Due to disruption in supply line, our originally ordered tablets were unable to arrive in time for launch and should come in a few weeks after launch. |  |  | 2 | bar: WEEK 5 T to WEEK 5 W

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Procure Tablets
Work with GM @ Downtown location to identiy number of tablets needed. |  | 0 | 0 | 0 | 1 | H
Work with GM @ North location to identify number of tablets needed. |  | 0 | 0 | 0 | 1 | H
Determine if we will purchase and store backup tablets for emergencies |  | 0 | 0 | 0 | 1 | H
Assess available tablet options and specs from the supplier that meet requirements. |  | 1 | 1 | 1 | 2 | H
Create contract and statements of work for tablet vendor |  | 2 | 1 | 2 | 3 | H
Buy and receive the correct number of tablets | Due to disruption in supply line, our originally ordered tablets were unable to arrive in time for launch and should come in a few weeks after launch. | 10 | 7 | 10 | 14 | H
Milestone: Installation and setup
Connect marketing team with Terrific Tablets for branding and digital menu design |  | 0 | 0 | 0 | 1 | H
Work with tablet supplier to identify common issues and turn-around times resolving tablet problems. |  | 2 | 1 | 2 | 4 | H
Develop internal policy and troubleshooting guides for the tablet rollout and usage |  | 3 | 1 | 2 | 4 | M
Assess work required to ensure tablets integrate seamlessly with existing POS and host system | In order to work with the tablets, the FlatPlate OS needs to be on version 3.0 | 3 | 1 | 3 | 4 | L
Identify a location to store backup tablets |  | 0 | 0 | 0 | 1 | H
Identify bar section tables that need to be wired properly by electrician |  | 0 | 0 | 0 | 1 | H
Install one tablet to ensure proper installation and to identify any potential issues |  | 0 | 0 | 0 | 1 | M
Hire electrician to wire appropriate tables at Downtown location | half-days. Let's address any potential issues by intsalling one tablet first and note any issues. | 3 | 2 | 3 | 4 | M
Hire electrician to wire appropriate tables at North location | half-days | 3 | 2 | 3 | 4 | M
Add featured menu items and coupon values to tablets | Dependent on marketing team designs, as well as identifying featured menu items and coupon values from Peta. Would also be impacted by potential menu revamp from Carter. | 1 | 0 | 1 | 2 | M
Work with BBB on possible menu revamp | Is this something that we can hold off on? It potentially blocks the decision for featured menu items and coupon values to display on the tablets | 10 | 4 | 10 | 14 | M
Milestone: Tablet Training
Develop a training program and rollout guide |  | 7 | 7 | 7 | 10 | H
Pre-training meeting to introduce tablets and changes |  | 1 | 1 | 1 | 2 | H
Seydou will train GMs and key staff on tablets |  | 2 | 2 | 2 | 3 | H
Work with GMs to coordinate, schedule, and hold meetings to discuss rollout and report questions/concerns | Be sure to monitor staff response and address any questions | 7 | 7 | 10 | 14 | L
Milestone: Test Run
Hold test run with staff family and friends in order to mimic full service |  | 0 | 0 | 0 | 1 | H
Collect feedback from test run and identify ways to improve |  | 1 | 0 | 1 | 2 | M
Implement feedback from test run | Not sure what these tasks might look like... they might range from updating menu to process change | 3 | 1 | 2 | 4 | L
Milestone: Launch Day
Schedule launch day |  | 0 | 0 | 0 | 1 | H
Prepare for launch day by coordinating and identifying outstanding needs from GMs |  | 2 | 1 | 2 | 4 | H
Launch day :D |  | 0 | 0 | 0 | 0 | H
Milestone: Install Upgraded Devices Post-Launch | Due to disruption in supply line, our originally ordered tablets were unable to arrive in time for launch and should come in a few weeks after launch.
Change plugs for new tablets.

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Restaurant Tablets- Is It Worth the Investment? | https://plumpos.com/restaurant-technology/restaurant-tablets.html | 2021-06-15 | Source kitchen monitors to streamline orders to allow the entire kitchen staff to view incoming requests without the struggle of deciphering different servers' handwriting
3 reasons why a tablet ordering system will ruin your restaurant | https://missdetails.com/3-reasons-why-a-tablet-ordering-system-will-ruin-your-restaurant/ | 2021-06-15 | Purchase backup tablets. What happens when a tablet breaks?

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction - faster, more efficient experience | Average ticket time for appetizers ~ 8 minutes and 12-15 minutes for entrees. | Can the back-end staff reasonably accomodate a turn-around time of around eight minutes for appetizers and 12-15 minutes for entrees? | Assess order flow and fulfillment. Track time orders are placed to when they are served. Does the tablet software track this data over time? | FALSE
Customer Satisfaction - faster, more efficient experience | Checkout time of one minute or less. | What are the benefits to customer experience when they are able to checkout in one minute or less? | Include optional surevy at the end of payment to collect user feedback | FALSE
Customer Satisfaction - faster, more efficient experience | Less than 5% of customers who use the tablets report technical issues each week | What are the common technical issues that arise with tablet usage and how can they be mitigated/avoided/resolved? | Research frequent tablet issues and identify ways to approach those issues should they arise. Train staff on those issues and how to resolve. | FALSE
Customer Satisfaction - faster, more efficient experience | 100% order accuracy |  |  | FALSE
Customer Satisfaction - faster, more efficient experience | Average wait time of ten minutes or less before customers are seated | How can we reduce the wait time to under ten minutes? | Track wait times in host system to ensure customers are being seated in under ten minutes. | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time for appetizers ~ 8 minutes and 12-15 minutes for entrees. | Can the back-end staff reasonably accomodate a turn-around time of around eight minutes for appetizers and 12-15 minutes for entrees? | Assess order flow and fulfillment. Track time orders are placed to when they are served. Does the tablet software track this data over time? | How long did it take for you to receive your appetizers? | Multiple choice | 5-10 minutes | 10-15 minutes | more than 15 minutes
Average ticket time for appetizers ~ 8 minutes and 12-15 minutes for entrees. | Can the back-end staff reasonably accomodate a turn-around time of around eight minutes for appetizers and 12-15 minutes for entrees? | Assess order flow and fulfillment. Track time orders are placed to when they are served. Does the tablet software track this data over time? | How long did it take for you to receive your entrees? | Multiple choice | 5-10 minutes | 10-15 minutes | more than 15 minutes
Checkout time of one minute or less. | What are the benefits to customer experience when they are able to checkout in one minute or less? | Include optional surevy at the end of payment to collect user feedback | How long did it take you to complete the checkout process today? | Multiple choice | less than a minute | 1-3 minutes | more than 3 minutes
Checkout time of one minute or less. | What are the benefits to customer experience when they are able to checkout in one minute or less? | Include optional surevy at the end of payment to collect user feedback | How satisfied are you using the tablet to checkout? | Scaled | Very Unsatisfied | Unsatisfied | Neutral | Satisfied | Very Satisfied
Less than 5% of customers who use the tablets report technical issues each week | What are the common technical issues that arise with tablet usage and how can they be mitigated/avoided/resolved? | Research frequent tablet issues and identify ways to approach those issues should they arise. Train staff on those issues and how to resolve. | Did you encounter any issues using the tablet? | Yes/No | Yes. Please explain: | No
Less than 5% of customers who use the tablets report technical issues each week | What are the common technical issues that arise with tablet usage and how can they be mitigated/avoided/resolved? | Research frequent tablet issues and identify ways to approach those issues should they arise. Train staff on those issues and how to resolve. | How was your experience using the tablet to order your meal today? | Open-ended | Please explain:
100% order accuracy | How can we assess customer satisfaction with their meal? | Ask customer via survey if they enjoyed their meal and if they were able to order exactly what they wanted with the tablet | Were you satisfied with your meal today? | Yes/No | Yes | No
100% order accuracy | How can we assess customer satisfaction with their meal? | Ask customer via survey if they enjoyed their meal and if they were able to order exactly what they wanted with the tablet | Were you able to order exactly what you wanted? If no, please explain. | Yes/No | Yes | No. Please explain:
Average wait time of ten minutes or less before customers are seated | How can we reduce the wait time to under ten minutes? | Track wait times in host system to ensure customers are being seated in under ten minutes. | How long did you have to wait before being seated today? | Multiple choice | 0-5 min | 5-10 min | 10-15min | 15 or more min
Average wait time of ten minutes or less before customers are seated | How can we reduce the wait time to under ten minutes? | Track wait times in host system to ensure customers are being seated in under ten minutes. | Were you satisfied with your wait time today? | Scaled | Very Unsatisfied | Unsatisfied | Neutral | Satisfied | Very Satisfied